## Sheet1
Document Title | TenneT Doc.-ID | Send Date cur. Revision | Rev-Vers | Review Status | Handover to ADM | Interface Document for | PDF Format | Original Format | Current Official Review Protocol | Previous Official Review Protocols | Related Document Comments | TenneT-Review Due Date | Responsible | Contract/Lot | Payment Milestone | Contractor Review Due Date | Distribution Code | F0 - Main Function | F1 - System / Subsystem | F2 - Basic Function | P1 - Product | P2 - Product | Item Designation | DCC - Technical Area | DCC -A2A3nnn_[V/A/T]- Sub Class-No. | Originator Doc.-ID | Purpose of Issue | Purpose of Submission | Book | CA Review Status | Certifying Authority (CA) | Preliminary as built file | Sheet No. | Prev. Company Review Status | Sender cur. Version | Item Designation Complete | Related Certification Reply Sheet | Submission to TenneT: Status | Submission Timestamp | Send Date cur. Version | Certifying Agency Doc. Container Number | Prev. Purpose of Submission
HEATER & TRACE HEATING EQUIPMENT O&M MANUAL | XXXX-XXX-00730-001 | 2022-05-18 | 03-v001 | Unchecked | -/- | 000-Without | XXXX-XXX-00730-001-MA-EN_03--HEATER & TRACE HEATING EQUIPMENT O&M MANUAL.pdf (1.0MB ^) | XXXX-XXX-00730-001-MA-EN_03--HEATER & TRACE HEATING EQUIPMENT O&M MANUAL.docx (4.4MB ^) | -/- | -/- |  | -/- | Max Mustermann | Platform | NA-without | -/- | OAM-Operation and Maintenance | '=T001-=T001 | - =T001.AZA10-AZA10 - =T001.AXG20-AXG20 - =T001.AXG10-AXG10 - =T001.AXD30-AXD30 - =T001.AXA10-AXA10 | - =T001.AZA10.EB003-EB003 - =T001.AZA10.EB002-EB002 - =T001.AZA10.EB001-EB001 - =T001.AXG20.WP066-WP066 - =T001.AXG20.WP065-WP065 - =T001.AXG20.WP015-WP015 - =T001.AXG10.WP049-WP049 - =T001.AXG10.WP048-WP048 - =T001.AXG10.WP026-WP026 - =T001.AXG10.WP025-WP025 - =T001.AXG10.WP024-WP024 - =T001.AXG10.WP023-WP023 - =T001.AXG10.EB001-EB001 - =T001.AXD30.WP018-WP018 - =T001.AXA10.EZ046-EZ046 - =T001.AXA10.EZ045-EZ045 - =T001.AXA10.EZ044-EZ044 - =T001.AXA10.EZ043-EZ043 - =T001.AXA10.EZ042-EZ042 - =T001.AXA10.EZ041-EZ041 - =T001.AXA10.EZ040-EZ040 - =T001.AXA10.EZ039-EZ039 - =T001.AXA10.EZ038-EZ038 - =T001.AXA10.EZ036-EZ036 - =T001.AXA10.EZ035-EZ035 - =T001.AXA10.EZ033-EZ033 - =T001.AXA10.EZ032-EZ032 - =T001.AXA10.EZ030-EZ030 - =T001.AXA10.EZ029-EZ029 - =T001.AXA10.EZ028-EZ028 - =T001.AXA10.EZ027-EZ027 - =T001.AXA10.EZ026-EZ026 - =T001.AXA10.EZ025-EZ025 - =T001.AXA10.EZ024-EZ024 - =T001.AXA10.EZ023-EZ023 - =T001.AXA10.EZ022-EZ022 - =T001.AXA10.EZ021-EZ021 - =T001.AXA10.EZ020-EZ020 - =T001.AXA10.EZ019-EZ019 - =T001.AXA10.EZ018-EZ018 - =T001.AXA10.EZ017-EZ017 - =T001.AXA10.EZ016-EZ016 - =T001.AXA10.EZ015-EZ015 - =T001.AXA10.EZ013-EZ013 - =T001.AXA10.EZ012-EZ012 - =T001.AXA10.EZ011-EZ011 - =T001.AXA10.EZ010-EZ010 - =T001.AXA10.EZ009-EZ009 - =T001.AXA10.EZ008-EZ008 - =T001.AXA10.EZ007-EZ007 - =T001.AXA10.EZ005-EZ005 - =T001.AXA10.EZ004-EZ004 - =T001.AXA10.EZ002-EZ002 - =T001.AXA10.EZ001-EZ001 - =T001.AXA10.EB007-EB007 - =T001.AXA10.EB006-EB006 - =T001.AXA10.EB005-EB005 - =T001.AXA10.EB004-EB004 - =T001.AXA10.EB003-EB003 - =T001.AXA10.EB002-EB002 - =T001.AXA10.EB001-EB001 | - =T001.AZA10.EB003.-EB001--EB001 - =T001.AZA10.EB002.-EB001--EB001 - =T001.AZA10.EB001.-EB001--EB001 - =T001.AXG20.WP066.-WP001--WP001 - =T001.AXG20.WP065.-WP001--WP001 - =T001.AXG20.WP015.-WP001--WP001 - =T001.AXG10.WP049.-WP001--WP001 - =T001.AXG10.WP048.-WP001--WP001 - =T001.AXG10.WP026.-WP001--WP001 - =T001.AXG10.WP025.-WP001--WP001 - =T001.AXG10.WP024.-WP001--WP001 - =T001.AXG10.WP023.-WP001--WP001 - =T001.AXG10.EB001.-EB001--EB001 - =T001.AXD30.WP018.-WP001--WP001 - =T001.AXA10.EZ046.-EB001--EB001 - =T001.AXA10.EZ045.-EB001--EB001 - =T001.AXA10.EZ044.-EB001--EB001 - =T001.AXA10.EZ043.-EB001--EB001 - =T001.AXA10.EZ042.-EB001--EB001 - =T001.AXA10.EZ041.-EB001--EB001 - =T001.AXA10.EZ040.-EB001--EB001 - =T001.AXA10.EZ039.-EB001--EB001 - =T001.AXA10.EZ038.-EB001--EB001 - =T001.AXA10.EZ036.-EB001--EB001 - =T001.AXA10.EZ035.-EB001--EB001 - =T001.AXA10.EZ033.-EB001--EB001 - =T001.AXA10.EZ032.-EB001--EB001 - =T001.AXA10.EZ030.-EB001--EB001 - =T001.AXA10.EZ029.-EB001--EB001 - =T001.AXA10.EZ028.-EB001--EB001 - =T001.AXA10.EZ027.-EB001--EB001 - =T001.AXA10.EZ026.-EB001--EB001 - =T001.AXA10.EZ025.-EB001--EB001 - =T001.AXA10.EZ024.-EB001--EB001 - =T001.AXA10.EZ023.-EB001--EB001 - =T001.AXA10.EZ022.-EB001--EB001 - =T001.AXA10.EZ021.-EB001--EB001 - =T001.AXA10.EZ020.-EB001--EB001 - =T001.AXA10.EZ019.-EB001--EB001 - =T001.AXA10.EZ018.-EB001--EB001 - =T001.AXA10.EZ017.-EB001--EB001 - =T001.AXA10.EZ016.-EB001--EB001 - =T001.AXA10.EZ015.-EB001--EB001 - =T001.AXA10.EZ013.-EB001--EB001 - =T001.AXA10.EZ012.-EB001--EB001 - =T001.AXA10.EZ011.-EB001--EB001 - =T001.AXA10.EZ010.-EB001--EB001 - =T001.AXA10.EZ009.-EB001--EB001 - =T001.AXA10.EZ008.-EB001--EB001 - =T001.AXA10.EZ007.-EB001--EB001 - =T001.AXA10.EZ005.-EB001--EB001 - =T001.AXA10.EZ004.-EB001--EB001 - =T001.AXA10.EZ002.-EB001--EB001 - =T001.AXA10.EZ001.-EB001--EB001 - =T001.AXA10.EB007.-EB001--EB001 - =T001.AXA10.EB006.-EB001--EB001 - =T001.AXA10.EB005.-EB001--EB001 - =T001.AXA10.EB004.-EB001--EB001 - =T001.AXA10.EB003.-EB001--EB001 - =T001.AXA10.EB002.-EB030--EB030 - =T001.AXA10.EB002.-EB020--EB020 - =T001.AXA10.EB002.-EB010--EB010 - =T001.AXA10.EB001.-EB030--EB030 - =T001.AXA10.EB001.-EB020--EB020 - =T001.AXA10.EB001.-EB010--EB010 | -/- | - =T001 AZA10 EB003-EB001 - ELECTRIC HEATER - =T001 AZA10 EB002-EB001 - ELECTRIC HEATER - =T001 AZA10 EB001-EB001 - ELECTRIC HEATER - =T001 AXG20 WP066-WP001 - DRAIN SEAL - =T001 AXG20 WP065-WP001 - DRAIN SEAL - =T001 AXG20 WP015-WP001 - DRAIN LINE - =T001 AXG10 WP049-WP001 - DRAIN SEAL - =T001 AXG10 WP048-WP001 - DRAIN SEAL - =T001 AXG10 WP026-WP001 - DRAIN LINE - =T001 AXG10 WP025-WP001 - DRAIN LINE - =T001 AXG10 WP024-WP001 - DRAIN TRANSFER PUMP 2 INLET LINE - =T001 AXG10 WP023-WP001 - DRAIN TRANSFER PUMP 1 INLET LINE - =T001 AXG10 EB001-EB001 - HEATER - =T001 AXD30 WP018-WP001 - FRESH WATER DISTRIBUTION - =T001 AXA10 EZ046-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ045-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ044-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ043-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ042-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ041-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ040-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ039-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ038-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ036-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ035-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ033-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ032-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ030-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ029-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ028-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ027-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ026-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ025-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ024-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ023-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ022-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ021-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ020-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ019-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ018-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ017-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ016-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ015-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ013-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ012-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ011-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ010-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ009-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ008-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ007-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ005-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ004-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ002-EB001 - ELECTRIC HEATER - =T001 AXA10 EZ001-EB001 - ELECTRIC HEATER - =T001 AXA10 EB007-EB001 - HEATER - =T001 AXA10 EB006-EB001 - HEATER - =T001 AXA10 EB005-EB001 - HEATER - =T001 AXA10 EB004-EB001 - HEATER - =T001 AXA10 EB003-EB001 - HEATER - =T001 AXA10 EB002-EB030 - ELECTRICAL HEATER STAGE 3 - =T001 AXA10 EB002-EB020 - ELECTRICAL HEATER STAGE 2 - =T001 AXA10 EB002-EB010 - ELECTRICAL HEATER STAGE 1 - =T001 AXA10 EB001-EB030 - ELECTRICAL HEATER STAGE 3 - =T001 AXA10 EB001-EB020 - ELECTRICAL HEATER STAGE 2 - =T001 AXA10 EB001-EB010 - ELECTRICAL HEATER STAGE 1 | B - Overall technology | DC090-Maintenance manual | OS00008-E-T001-OP-MLD-14760 | Issued As-Final | For information | B6-User Instructions and Manuals | -/- | -/- | -/- | 001 | -/- | John Doe | '=T001 AZA10 EB003-EB001 - ELECTRIC HEATER =T001 AZA10 EB002-EB001 - ELECTRIC HEATER =T001 AZA10 EB001-EB001 - ELECTRIC HEATER =T001 AXG20 WP066-WP001 - DRAIN SEAL =T001 AXG20 WP065-WP001 - DRAIN SEAL =T001 AXG20 WP015-WP001 - DRAIN LINE =T001 AXG10 WP049-WP001 - DRAIN SEAL =T001 AXG10 WP048-WP001 - DRAIN SEAL =T001 AXG10 WP026-WP001 - DRAIN LINE =T001 AXG10 WP025-WP001 - DRAIN LINE =T001 AXG10 WP024-WP001 - DRAIN TRANSFER PUMP 2 INLET LINE =T001 AXG10 WP023-WP001 - DRAIN TRANSFER PUMP 1 INLET LINE =T001 AXG10 EB001-EB001 - HEATER =T001 AXD30 WP018-WP001 - FRESH WATER DISTRIBUTION =T001 AXA10 EZ046-EB001 - ELECTRIC HEATER =T001 AXA10 EZ045-EB001 - ELECTRIC HEATER =T001 AXA10 EZ044-EB001 - ELECTRIC HEATER =T001 AXA10 EZ043-EB001 - ELECTRIC HEATER =T001 AXA10 EZ042-EB001 - ELECTRIC HEATER =T001 AXA10 EZ041-EB001 - ELECTRIC HEATER =T001 AXA10 EZ040-EB001 - ELECTRIC HEATER =T001 AXA10 EZ039-EB001 - ELECTRIC HEATER =T001 AXA10 EZ038-EB001 - ELECTRIC HEATER =T001 AXA10 EZ036-EB001 - ELECTRIC HEATER =T001 AXA10 EZ035-EB001 - ELECTRIC HEATER =T001 AXA10 EZ033-EB001 - ELECTRIC HEATER =T001 AXA10 EZ032-EB001 - ELECTRIC HEATER =T001 AXA10 EZ030-EB001 - ELECTRIC HEATER =T001 AXA10 EZ029-EB001 - ELECTRIC HEATER =T001 AXA10 EZ028-EB001 - ELECTRIC HEATER =T001 AXA10 EZ027-EB001 - ELECTRIC HEATER =T001 AXA10 EZ026-EB001 - ELECTRIC HEATER =T001 AXA10 EZ025-EB001 - ELECTRIC HEATER =T001 AXA10 EZ024-EB001 - ELECTRIC HEATER =T001 AXA10 EZ023-EB001 - ELECTRIC HEATER =T001 AXA10 EZ022-EB001 - ELECTRIC HEATER =T001 AXA10 EZ021-EB001 - ELECTRIC HEATER =T001 AXA10 EZ020-EB001 - ELECTRIC HEATER =T001 AXA10 EZ019-EB001 - ELECTRIC HEATER =T001 AXA10 EZ018-EB001 - ELECTRIC HEATER =T001 AXA10 EZ017-EB001 - ELECTRIC HEATER =T001 AXA10 EZ016-EB001 - ELECTRIC HEATER =T001 AXA10 EZ015-EB001 - ELECTRIC HEATER =T001 AXA10 EZ013-EB001 - ELECTRIC HEATER =T001 AXA10 EZ012-EB001 - ELECTRIC HEATER =T001 AXA10 EZ011-EB001 - ELECTRIC HEATER =T001 AXA10 EZ010-EB001 - ELECTRIC HEATER =T001 AXA10 EZ009-EB001 - ELECTRIC HEATER =T001 AXA10 EZ008-EB001 - ELECTRIC HEATER =T001 AXA10 EZ007-EB001 - ELECTRIC HEATER =T001 AXA10 EZ005-EB001 - ELECTRIC HEATER =T001 AXA10 EZ004-EB001 - ELECTRIC HEATER =T001 AXA10 EZ002-EB001 - ELECTRIC HEATER =T001 AXA10 EZ001-EB001 - ELECTRIC HEATER =T001 AXA10 EB007-EB001 - HEATER =T001 AXA10 EB006-EB001 - HEATER =T001 AXA10 EB005-EB001 - HEATER =T001 AXA10 EB004-EB001 - HEATER =T001 AXA10 EB003-EB001 - HEATER =T001 AXA10 EB002-EB030 - ELECTRICAL HEATER STAGE 3 =T001 AXA10 EB002-EB020 - ELECTRICAL HEATER STAGE 2 =T001 AXA10 EB002-EB010 - ELECTRICAL HEATER STAGE 1 =T001 AXA10 EB001-EB030 - ELECTRICAL HEATER STAGE 3 =T001 AXA10 EB001-EB020 - ELECTRICAL HEATER STAGE 2 =T001 AXA10 EB001-EB010 - ELECTRICAL HEATER STAGE 1 | Related Certification Reply Sheet | Not submitted | -/- | 2022-05-19 | NA | -/-
P&ID - FRESH WATER DISTRIBUTION | XXXX-XXX-01130-002 | 2023-03-24 | 06-v001 | Unchecked | -/- | 000-Without | XXXX-XXX-01130-002-MA-EN_06--P&ID - FRESH WATER DISTRIBUTION.pdf (1.0MB ^) | -/- | -/- | -/- |  | 2023-04-19 | John Doe | Platform | NA-without | -/- | PME-Platform Mechanical | '=T001-=T001 | - =T001.AZA10-AZA10 - =T001.AXD30-AXD30 | - =T001.AZA10.VQ012-VQ012 - =T001.AZA10.VQ011-VQ011 - =T001.AZA10.VQ010-VQ010 - =T001.AZA10.VQ009-VQ009 - =T001.AZA10.VQ008-VQ008 - =T001.AZA10.VQ007-VQ007 - =T001.AZA10.VQ001-VQ001 - =T001.AZA10.EB003-EB003 - =T001.AZA10.EB002-EB002 - =T001.AZA10.EB001-EB001 - =T001.AXD30.WP117-WP117 - =T001.AXD30.WP116-WP116 - =T001.AXD30.WP115-WP115 - =T001.AXD30.WP114-WP114 - =T001.AXD30.WP113-WP113 - =T001.AXD30.WP112-WP112 - =T001.AXD30.WP111-WP111 - =T001.AXD30.WP110-WP110 - =T001.AXD30.WP109-WP109 - =T001.AXD30.WP108-WP108 - =T001.AXD30.WP107-WP107 - =T001.AXD30.WP106-WP106 - =T001.AXD30.WP105-WP105 - =T001.AXD30.WP104-WP104 - =T001.AXD30.WP103-WP103 - =T001.AXD30.WP102-WP102 - =T001.AXD30.WP101-WP101 | - =T001.AZA10.VQ012.-VQ001--VQ001 - =T001.AZA10.VQ011.-VQ001--VQ001 - =T001.AZA10.VQ010.-VQ001--VQ001 - =T001.AZA10.VQ009.-VQ001--VQ001 - =T001.AZA10.VQ008.-VQ001--VQ001 - =T001.AZA10.VQ007.-VQ001--VQ001 - =T001.AZA10.VQ001.-VQ006--VQ006 - =T001.AZA10.VQ001.-VQ005--VQ005 - =T001.AZA10.VQ001.-VQ004--VQ004 - =T001.AZA10.VQ001.-VQ003--VQ003 - =T001.AZA10.VQ001.-VQ002--VQ002 - =T001.AZA10.VQ001.-VQ001--VQ001 - =T001.AZA10.EB003.-EB001--EB001 - =T001.AZA10.EB002.-EB001--EB001 - =T001.AZA10.EB001.-EB001--EB001 - =T001.AXD30.WP117.-QM001--QM001 - =T001.AXD30.WP116.-WP001--WP001 - =T001.AXD30.WP116.-RM001--RM001 - =T001.AXD30.WP116.-QM004--QM004 - =T001.AXD30.WP116.-QM003--QM003 - =T001.AXD30.WP116.-QM002--QM002 - =T001.AXD30.WP116.-QM001--QM001 - =T001.AXD30.WP115.-WP001--WP001 - =T001.AXD30.WP115.-RM001--RM001 - =T001.AXD30.WP115.-QM004--QM004 - =T001.AXD30.WP115.-QM003--QM003 - =T001.AXD30.WP115.-QM002--QM002 - =T001.AXD30.WP115.-QM001--QM001 - =T001.AXD30.WP114.-WP001--WP001 - =T001.AXD30.WP114.-RM001--RM001 - =T001.AXD30.WP114.-QM004--QM004 - =T001.AXD30.WP114.-QM003--QM003 - =T001.AXD30.WP114.-QM002--QM002 - =T001.AXD30.WP114.-QM001--QM001 - =T001.AXD30.WP113.-WP001--WP001 - =T001.AXD30.WP113.-QM003--QM003 - =T001.AXD30.WP113.-QM002--QM002 - =T001.AXD30.WP113.-QM001--QM001 - =T001.AXD30.WP112.-WP001--WP001 - =T001.AXD30.WP112.-RM001--RM001 - =T001.AXD30.WP112.-QM002--QM002 - =T001.AXD30.WP112.-QM001--QM001 - =T001.AXD30.WP111.-WP001--WP001 - =T001.AXD30.WP111.-QM001--QM001 - =T001.AXD30.WP110.-WP001--WP001 - =T001.AXD30.WP110.-QM001--QM001 - =T001.AXD30.WP109.-WP001--WP001 - =T001.AXD30.WP109.-RM001--RM001 - =T001.AXD30.WP109.-QM005--QM005 - =T001.AXD30.WP109.-QM004--QM004 - =T001.AXD30.WP109.-QM003--QM003 - =T001.AXD30.WP109.-QM002--QM002 - =T001.AXD30.WP109.-QM001--QM001 - =T001.AXD30.WP108.-WP001--WP001 - =T001.AXD30.WP108.-RM001--RM001 - =T001.AXD30.WP108.-QM001--QM001 - =T001.AXD30.WP107.-WP001--WP001 - =T001.AXD30.WP107.-RM001--RM001 - =T001.AXD30.WP107.-QM001--QM001 - =T001.AXD30.WP106.-WP001--WP001 - =T001.AXD30.WP105.-WP001--WP001 - =T001.AXD30.WP104.-WP001--WP001 - =T001.AXD30.WP104.-RM001--RM001 - =T001.AXD30.WP104.-QM004--QM004 - =T001.AXD30.WP104.-QM003--QM003 - =T001.AXD30.WP104.-QM002--QM002 - =T001.AXD30.WP104.-QM001--QM001 - =T001.AXD30.WP103.-WP001--WP001 - =T001.AXD30.WP103.-RM001--RM001 - =T001.AXD30.WP103.-QM004--QM004 - =T001.AXD30.WP103.-QM003--QM003 - =T001.AXD30.WP103.-QM002--QM002 - =T001.AXD30.WP103.-QM001--QM001 - =T001.AXD30.WP102.-WP001--WP001 - =T001.AXD30.WP101.-WP001--WP001 | -/- | - =T001 AZA10 VQ012-VQ001 - FAUCET - =T001 AZA10 VQ011-VQ001 - FAUCET - =T001 AZA10 VQ010-VQ001 - FAUCET - =T001 AZA10 VQ009-VQ001 - FAUCET - =T001 AZA10 VQ008-VQ001 - FAUCET - =T001 AZA10 VQ007-VQ001 - FAUCET - =T001 AZA10 VQ001-VQ006 - WASH BASIN AT MESS - =T001 AZA10 VQ001-VQ005 - SHOWER SET - =T001 AZA10 VQ001-VQ004 - WASH BASIN AT TOILET - =T001 AZA10 VQ001-VQ003 - WASH BASIN AT CHANGE ROOM - =T001 AZA10 VQ001-VQ002 - WASH BASIN AT CHANGE ROOM - =T001 AZA10 VQ001-VQ001 - WASH BASIN AT WORKSHOP ROOM - =T001 AZA10 EB003-EB001 - ELECTRIC HEATER - =T001 AZA10 EB002-EB001 - ELECTRIC HEATER - =T001 AZA10 EB001-EB001 - ELECTRIC HEATER - =T001 AXD30 WP117-QM001 - MANUAL VALVE - =T001 AXD30 WP116-WP001 - FRESH WATER LINE - =T001 AXD30 WP116-RM001 - CHECK VALVE - =T001 AXD30 WP116-QM004 - DRAIN VALVE - =T001 AXD30 WP116-QM003 - DRAIN VALVE - =T001 AXD30 WP116-QM002 - DRAIN VALVE - =T001 AXD30 WP116-QM001 - MANUAL VALVE - =T001 AXD30 WP115-WP001 - FRESH WATER LINE - =T001 AXD30 WP115-RM001 - CHECK VALVE - =T001 AXD30 WP115-QM004 - DRAIN VALVE - =T001 AXD30 WP115-QM003 - DRAIN VALVE - =T001 AXD30 WP115-QM002 - DRAIN VALVE - =T001 AXD30 WP115-QM001 - MANUAL VALVE - =T001 AXD30 WP114-WP001 - FRESH WATER LINE - =T001 AXD30 WP114-RM001 - CHECK VALVE - =T001 AXD30 WP114-QM004 - DRAIN VALVE - =T001 AXD30 WP114-QM003 - DRAIN VALVE - =T001 AXD30 WP114-QM002 - DRAIN VALVE - =T001 AXD30 WP114-QM001 - MANUAL VALVE - =T001 AXD30 WP113-WP001 - FRESH WATER LINE - =T001 AXD30 WP113-QM003 - DRAIN VALVE - =T001 AXD30 WP113-QM002 - DRAIN VALVE - =T001 AXD30 WP113-QM001 - MANUAL VALVE - =T001 AXD30 WP112-WP001 - FRESH WATER LINE - =T001 AXD30 WP112-RM001 - CHECK VALVE - =T001 AXD30 WP112-QM002 - DRAIN VALVE - =T001 AXD30 WP112-QM001 - MANUAL VALVE - =T001 AXD30 WP111-WP001 - FRESH WATER LINE - =T001 AXD30 WP111-QM001 - MANUAL VALVE - =T001 AXD30 WP110-WP001 - FRESH WATER LINE - =T001 AXD30 WP110-QM001 - MANUAL VALVE - =T001 AXD30 WP109-WP001 - FRESH WATER LINE - =T001 AXD30 WP109-RM001 - CHECK VALVE - =T001 AXD30 WP109-QM005 - DRAIN VALVE - =T001 AXD30 WP109-QM004 - DRAIN VALVE - =T001 AXD30 WP109-QM003 - DRAIN VALVE - =T001 AXD30 WP109-QM002 - DRAIN VALVE - =T001 AXD30 WP109-QM001 - MANUAL VALVE - =T001 AXD30 WP108-WP001 - FRESH WATER LINE - =T001 AXD30 WP108-RM001 - CHECK VALVE - =T001 AXD30 WP108-QM001 - MANUAL VALVE - =T001 AXD30 WP107-WP001 - FRESH WATER LINE - =T001 AXD30 WP107-RM001 - CHECK VALVE - =T001 AXD30 WP107-QM001 - MANUAL VALVE - =T001 AXD30 WP106-WP001 - FRESH WATER LINE - =T001 AXD30 WP105-WP001 - FRESH WATER LINE - =T001 AXD30 WP104-WP001 - FRESH WATER LINE - =T001 AXD30 WP104-RM001 - CHECK VALVE - =T001 AXD30 WP104-QM004 - DRAIN VALVE - =T001 AXD30 WP104-QM003 - DRAIN VALVE - =T001 AXD30 WP104-QM002 - DRAIN VALVE - =T001 AXD30 WP104-QM001 - MANUAL VALVE - =T001 AXD30 WP103-WP001 - FRESH WATER LINE - =T001 AXD30 WP103-RM001 - CHECK VALVE - =T001 AXD30 WP103-QM004 - DRAIN VALVE - =T001 AXD30 WP103-QM003 - DRAIN VALVE - =T001 AXD30 WP103-QM002 - DRAIN VALVE - =T001 AXD30 WP103-QM001 - MANUAL VALVE - =T001 AXD30 WP102-WP001 - FRESH WATER LINE - =T001 AXD30 WP101-WP001 - FRESH WATER LINE | M - Mechanical engineering | FB030-Piping and instrument diagram (P&ID) | OS00008-E-T001-PI-PID-34009 | Issued for Design | For Review | B5b-Design- and Construction Documentation - Systems | -/- | -/- | -/- | 002 | -/- | Jane Doe | -/- | Related Certification Reply Sheet | Not submitted | -/- | 2023-03-29 | NA | -/-
INSTRUMENT LOOP DRAWING | XXXX-XXX-01598-001 | 2021-11-08 | 01-v004 | Unchecked | -/- | 000-Without | XXXX-XXX-01598-001-MA-EN_01--INSTRUMENT LOOP DRAWING.pdf (324.4MB ^) | -/- | -/- | -/- |  | -/- | Jane Doe | Platform | NA-without | -/- | PCI-Platform Communication Instrumentation | - =T001-=T001 - =K001-=K001 | - =T001.AZA10-AZA10 - =T001.AYB10-AYB10 - =T001.AYA20-AYA20 - =T001.AXS20-AXS20 - =T001.AXJ10-AXJ10 - =T001.AXH60-AXH60 - =T001.AXH50-AXH50 - =T001.AXH40-AXH40 - =T001.AXH30-AXH30 - =T001.AXH20-AXH20 - =T001.AXH10-AXH10 - =T001.AXG10-AXG10 - =T001.AXD30-AXD30 - =T001.AXD20-AXD20 - =T001.AXB30-AXB30 - =T001.AXB20-AXB20 - =T001.AXB10-AXB10 - =T001.ANP20-ANP20 - =T001.ANP10-ANP10 - =T001.ANK20-ANK20 - =T001.ANK10-ANK10 - =T001.ANJ20-ANJ20 - =T001.ANJ10-ANJ10 - =T001.ANG20-ANG20 - =T001.ANG10-ANG10 - =T001.ANE40-ANE40 - =T001.ANE30-ANE30 - =T001.ANE20-ANE20 - =T001.ANE10-ANE10 - =T001.AFA41-AFA41 - =T001.AFA16-AFA16 - =T001.ADE20-ADE20 - =T001.ADE10-ADE10 - =T001.AAZ01-AAZ01 - =T001.AAF20-AAF20 - =K001.AAF30-AAF30 - =K001.AAF20-AAF20 - =K001.AAB10-AAB10 | -/- | -/- | -/- | - =T001 AZA10 - PLATFORM TOPSIDES - =T001 AYB10 - PUBLIC ANNOUNCEMENT AND GENERAL ALARM (PAGA) - =T001 AYA20 - VHF RADIO (INCLUDING RoIP) - =T001 AXS20 - MARINE NAVIGATION AIDS SYSTEM - =T001 AXJ10 - PORTABLE MATERIAL HANDLING EQUIPMENT - =T001 AXH60 - DAVIT CRANE 1 - =T001 AXH50 - DAVIT CRANE 1 - =T001 AXH40 - OVERHEAD CRANE 66KV GIS ROOM B - =T001 AXH30 - OVERHEAD CRANE 66KV GIS ROOM A - =T001 AXH20 - OVERHEAD CRANE 220KV GIS ROOM - =T001 AXH10 - PLATFORM MAIN CRANE - =T001 AXG10 - HAZARDOUS DRAIN SYSTEM - =T001 AXD30 - FRESH WATER SYSTEM - =T001 AXD20 - DECK WASH SYSTEM - =T001 AXB30 - FIRE ALARM SYSTEM (FAS) - =T001 AXB20 - FIRE EXTINGUISHING SYSTEM INERT GAS - =T001 AXB10 - FIRE EXTINGUISHING SYSTEM FOAM - =T001 ANP20 - 110V DC UPS SYSTEM 2 - =T001 ANP10 - 110V DC UPS SYSTEM 1 - =T001 ANK20 - 110V DC DISTRIBUTION SYSTEM 2 - =T001 ANK10 - 110V DC DISTRIBUTION SYSTEM 1 - =T001 ANJ20 - 230/400V AC UPS SYSTEM 2 - =T001 ANJ10 - 230/400V AC UPS SYSTEM 1 - =T001 ANG20 - DIESEL GENERATOR 2 (TEMPORARY) - =T001 ANG10 - DIESEL GENERATOR 1 (TEMPORARY) - =T001 ANE40 - 230/400V AC EMERGENCY DISTRIBUTION 2 SYSTEM - =T001 ANE30 - 230/400V AC EMERGENCY DISTRIBUTION 1 SYSTEM - =T001 ANE20 - 230/400V AC MAIN DISTRIBUTION 2 SYSTEM - =T001 ANE10 - 230/400V AC MAIN DISTRIBUTION 1 SYSTEM - =T001 AFA41 - 66KV GIS SYSTEM 4 - BAY-1 - =T001 AFA16 - 66KV GIS SYSTEM 1 - BAY-6 - =T001 ADE20 - 220KV SYSTEM 2 - =T001 ADE10 - 220KV SYSTEM 1 - =T001 AAZ01 - INTERFACE CABINET SYSTEM - =T001 AAF20 - AUXILIARY SCADA NETWORK SYSTEM - =K001 AAF30 - TENNET CONTROL ROOM - =K001 AAF20 - AUXILIARY SCADA NETWORK SYSTEM - =K001 AAB10 - HV HMI SYSTEM | E - Electrical engineering, instrumentation and control engineering | MA020-Terminal connection diagram | OS00008-E-T001-IC-LOP-54512 | Issued for Installation / Construction | For information | B5b-Design- and Construction Documentation - Systems | -/- | -/- | -/- | 001 | Unchecked | John Doe | '=T001 AZA10 - PLATFORM TOPSIDES =T001 AYB10 - PUBLIC ANNOUNCEMENT AND GENERAL ALARM (PAGA) =T001 AYA20 - VHF RADIO (INCLUDING RoIP) =T001 AXS20 - MARINE NAVIGATION AIDS SYSTEM =T001 AXJ10 - PORTABLE MATERIAL HANDLING EQUIPMENT =T001 AXH60 - DAVIT CRANE 1 =T001 AXH50 - DAVIT CRANE 1 =T001 AXH40 - OVERHEAD CRANE 66KV GIS ROOM B =T001 AXH30 - OVERHEAD CRANE 66KV GIS ROOM A =T001 AXH20 - OVERHEAD CRANE 220KV GIS ROOM =T001 AXH10 - PLATFORM MAIN CRANE =T001 AXG10 - HAZARDOUS DRAIN SYSTEM =T001 AXD30 - FRESH WATER SYSTEM =T001 AXD20 - DECK WASH SYSTEM =T001 AXB30 - FIRE ALARM SYSTEM (FAS) =T001 AXB20 - FIRE EXTINGUISHING SYSTEM INERT GAS =T001 AXB10 - FIRE EXTINGUISHING SYSTEM FOAM =T001 ANP20 - 110V DC UPS SYSTEM 2 =T001 ANP10 - 110V DC UPS SYSTEM 1 =T001 ANK20 - 110V DC DISTRIBUTION SYSTEM 2 =T001 ANK10 - 110V DC DISTRIBUTION SYSTEM 1 =T001 ANJ20 - 230/400V AC UPS SYSTEM 2 =T001 ANJ10 - 230/400V AC UPS SYSTEM 1 =T001 ANG20 - DIESEL GENERATOR 2 (TEMPORARY) =T001 ANG10 - DIESEL GENERATOR 1 (TEMPORARY) =T001 ANE40 - 230/400V AC EMERGENCY DISTRIBUTION 2 SYSTEM =T001 ANE30 - 230/400V AC EMERGENCY DISTRIBUTION 1 SYSTEM =T001 ANE20 - 230/400V AC MAIN DISTRIBUTION 2 SYSTEM =T001 ANE10 - 230/400V AC MAIN DISTRIBUTION 1 SYSTEM =T001 AFA41 - 66KV GIS SYSTEM 4 - BAY-1 =T001 AFA16 - 66KV GIS SYSTEM 1 - BAY-6 =T001 ADE20 - 220KV SYSTEM 2 =T001 ADE10 - 220KV SYSTEM 1 =T001 AAZ01 - INTERFACE CABINET SYSTEM =T001 AAF20 - AUXILIARY SCADA NETWORK SYSTEM =K001 AAF30 - TENNET CONTROL ROOM =K001 AAF20 - AUXILIARY SCADA NETWORK SYSTEM =K001 AAB10 - HV HMI SYSTEM | Related Certification Reply Sheet | Not submitted | -/- | 2022-10-14 | NA | For information
HVAC-ELECTRICAL & INTRUMENTATION EQUIPMENT LOCATION LAYOUT - CONTROL DECK | XXXX-XXX-02307-001 | 2022-05-20 | 04-v001 | Unchecked | -/- | 000-Without | XXXX-XXX-02307-001-MA-EN_04--HVAC-ELECTRICAL & INTRUMENTATION EQUIPMENT LOCATION LAYOUT - CONTROL DECK.pdf (3.4MB ^) | XXXX-XXX-02307-001-MA-EN_04--HVAC-ELECTRICAL & INTRUMENTATION EQUIPMENT LOCATION LAYOUT - CONTROL DECK.dwg (6.1MB ^) | -/- | -/- |  | -/- | John Doe | Platform | NA-without | -/- | PME-Platform Mechanical | '=T001-=T001 | - =T001.AZA10-AZA10 - =T001.AXY20-AXY20 - =T001.AXY10-AXY10 - =T001.AXA10-AXA10 | -/- | -/- | -/- | - =T001 AZA10 - PLATFORM TOPSIDES - =T001 AXY20 - CHILLED WATER SYSTEM - =T001 AXY10 - CLOSED COOLING SYSTEM - =T001 AXA10 - HVA/C SYSTEM | E - Electrical engineering, instrumentation and control engineering | LU010-Arrangement drawing (equipment) | OS00008-E-T001-EL-GAD-51502 | Issued As-Built | For information | B5b-Design- and Construction Documentation - Systems | -/- | -/- | -/- | 001 | -/- | Jane Doe | '=T001 AZA10 - PLATFORM TOPSIDES =T001 AXY20 - CHILLED WATER SYSTEM =T001 AXY10 - CLOSED COOLING SYSTEM =T001 AXA10 - HVA/C SYSTEM | Related Certification Reply Sheet | Not submitted | -/- | 2022-05-20 | NA | -/-
FURNITURE AND EQUIPMENT LAYOUT - WORKSHOP | XXXX-XXX-02333-001 | 2022-06-08 | 06-v001 | Unchecked | -/- | 000-Without | XXXX-XXX-02333-001-MA-EN_06--FURNITURE AND EQUIPMENT LAYOUT - WORKSHOP.pdf (920.3kB ^) | XXXX-XXX-02333-001-MA-EN_06--FURNITURE AND EQUIPMENT LAYOUT - WORKSHOP.dwg (3.2MB ^) | -/- | -/- |  | -/- | Max Mustermann | Platform | NA-without | -/- | PAR-Platform Architectural | '=T001-=T001 | - =T001.AZA10-AZA10 - =T001.AXJ10-AXJ10 - =T001.AXB30-AXB30 - =T001.AXB20-AXB20 - =T001.AXB10-AXB10 - =T001.AXA10-AXA10 - =T001.AXD20-AXD20 | - =T001.AZA10.VZ001-VZ001 - =T001.AZA10.VQ007-VQ007 - =T001.AZA10.VQ001-VQ001 - =T001.AZA10.UZ001-UZ001 - =T001.AZA10.PH011-PH011 - =T001.AZA10.GQ100-GQ100 - =T001.AZA10.EB001-EB001 - =T001.AZA10.CN006-CN006 - =T001.AZA10.CN005-CN005 - =T001.AZA10.CN004-CN004 - =T001.AZA10.CN003-CN003 - =T001.AZA10.CN002-CN002 - =T001.AZA10.CN001-CN001 - =T001.AZA10.CM015-CM015 - =T001.AZA10.CM014-CM014 - =T001.AZA10.CM013-CM013 - =T001.AZA10.BX001-BX001 - =T001.AZA10.BU001-BU001 - =T001.AXJ10.GU014-GU014 - =T001.AXJ10.GU013-GU013 - =T001.AXJ10.GU012-GU012 - =T001.AXJ10.GU011-GU011 - =T001.AXJ10.GU010-GU010 - =T001.AXJ10.GU005-GU005 - =T001.AXJ10.GU003-GU003 - =T001.AXJ10.GU002-GU002 - =T001.AXJ10.GU001-GU001 - =T001.AXJ10.GM009-GM009 - =T001.AXB30.XG001-XG001 - =T001.AXB30.XD016-XD016 - =T001.AXB20.XD015-XD015 - =T001.AXB10.XD005-XD005 - =T001.AXA10.XG046-XG046 - =T001.AXA10.XG033-XG033 - =T001.AXA10.XG015-XG015 - =T001.AXA10.XG014-XG014 - =T001.AXD20.GP002-GP002 - =T001.AXD20.GP001-GP001 | - =T001.AZA10.VZ001.-VZ001--VZ001 - =T001.AZA10.VQ007.-VQ001--VQ001 - =T001.AZA10.VQ001.-VQ001--VQ001 - =T001.AZA10.UZ001.-UZ006--UZ006 - =T001.AZA10.UZ001.-UZ005--UZ005 - =T001.AZA10.UZ001.-UZ004--UZ004 - =T001.AZA10.PH011.-PH001--PH001 - =T001.AZA10.GQ100.-GQ001--GQ001 - =T001.AZA10.EB001.-EB001--EB001 - =T001.AZA10.CN006.-CN001--CN001 - =T001.AZA10.CN005.-CN001--CN001 - =T001.AZA10.CN004.-CN001--CN001 - =T001.AZA10.CN003.-CN001--CN001 - =T001.AZA10.CN002.-CN001--CN001 - =T001.AZA10.CN001.-CN001--CN001 - =T001.AZA10.CM015.-CM001--CM001 - =T001.AZA10.CM014.-CM001--CM001 - =T001.AZA10.CM013.-CM001--CM001 - =T001.AZA10.BX001.-BX001--BX001 - =T001.AZA10.BU001.-BU001--BU001 - =T001.AXJ10.GU014.-GU001--GU001 - =T001.AXJ10.GU013.-GU001--GU001 - =T001.AXJ10.GU012.-GU001--GU001 - =T001.AXJ10.GU011.-GU001--GU001 - =T001.AXJ10.GU010.-GU001--GU001 - =T001.AXJ10.GU005.-GU001--GU001 - =T001.AXJ10.GU003.-GU001--GU001 - =T001.AXJ10.GU002.-GU001--GU001 - =T001.AXJ10.GU001.-GU001--GU001 - =T001.AXJ10.GM009.-GM001--GM001 - =T001.AXB30.XG001.-XG001--XG001 - =T001.AXB30.XD016.-XD001--XD001 - =T001.AXB20.XD015.-XD001--XD001 - =T001.AXB10.XD005.-XD001--XD001 - =T001.AXA10.XG046.-XG001--XG001 - =T001.AXA10.XG033.-XG001--XG001 - =T001.AXA10.XG015.-XG001--XG001 - =T001.AXA10.XG014.-XG001--XG001 | -/- | - =T001 AZA10 VZ001-VZ001 - DILO-CART - =T001 AZA10 VQ007-VQ001 - FAUCET - =T001 AZA10 VQ001-VQ001 - WASH BASIN AT WORKSHOP ROOM - =T001 AZA10 UZ001-UZ006 - PEGBOARD - =T001 AZA10 UZ001-UZ005 - STEEL WORKBENCH WITH TWO DRAWERS & WOODEN TOP-2 - =T001 AZA10 UZ001-UZ004 - STEEL WORKBENCH WITH TWO DRAWERS & WOODEN TOP-1 - =T001 AZA10 PH011-PH001 - DIGITAL STORAGE OSCILLOSCOPE - =T001 AZA10 GQ100-GQ001 - EXTRACTION HOOD - =T001 AZA10 EB001-EB001 - ELECTRIC HEATER - =T001 AZA10 CN006-CN001 - OIL DRUM - =T001 AZA10 CN005-CN001 - OIL DRUM - =T001 AZA10 CN004-CN001 - OIL DRUM - =T001 AZA10 CN003-CN001 - OIL DRUM - =T001 AZA10 CN002-CN001 - STANDARD TOOLSET - =T001 AZA10 CN001-CN001 - WASTE BIN - =T001 AZA10 CM015-CM001 - ATEX CABINET - =T001 AZA10 CM014-CM001 - STEEL CABINET - =T001 AZA10 CM013-CM001 - STEEL CABINET - =T001 AZA10 BX001-BX001 - PRM-6 PHASE SEQUENCE AND MOTOR ROTATION TESTER - =T001 AZA10 BU001-BU001 - DIGITAL MULTI METER - =T001 AXJ10 GU014-GU001 - TOOL TROLLEY - =T001 AXJ10 GU013-GU001 - TOOL TROLLEY - =T001 AXJ10 GU012-GU001 - TOOL TROLLEY - =T001 AXJ10 GU011-GU001 - TOOL TROLLEY - =T001 AXJ10 GU010-GU001 - DRUM TRUCK - =T001 AXJ10 GU005-GU001 - ELEVATING TROLLEY - =T001 AXJ10 GU003-GU001 - PALLET TRUCK - =T001 AXJ10 GU002-GU001 - CYLINDER TROLLEY - =T001 AXJ10 GU001-GU001 - TRANSPORTATION TROLLEY - =T001 AXJ10 GM009-GM001 - - =T001 AXB30 XG001-XG001 - JUNCTION BOX - =T001 AXB30 XD016-XD001 - JUNCTION BOX - =T001 AXB20 XD015-XD001 - JUNCTION BOX - =T001 AXB10 XD005-XD001 - JUNCTION BOX - =T001 AXA10 XG046-XG001 - JUNCTION BOX - =T001 AXA10 XG033-XG001 - JUNCTION BOX - =T001 AXA10 XG015-XG001 - JUNCTION BOX - =T001 AXA10 XG014-XG001 - JUNCTION BOX - =T001 AXD20 GP002 - HP CLEANING UNIT 2 - =T001 AXD20 GP001 - HP CLEANING UNIT 1 | M - Mechanical engineering | LU010-Arrangement drawing (equipment) | OS00008-E-T001-AR-LTD-47024 | Issued As-Built | For information | B5b-Design- and Construction Documentation - Systems | -/- | -/- | -/- | 001 | -/- | John Doe | -/- | Related Certification Reply Sheet | Not submitted | -/- | 2022-12-19 | NA | -/-
FRESH WATER PIPING LAYOUT - INVENTORY AND PUBLIC ROOMS | XXXX-XXX-02340-001 | 2022-05-23 | 01-v001 | Unchecked | -/- | 000-Without | XXXX-XXX-02340-001-MA-EN_01--FRESH WATER PIPING LAYOUT - INVENTORY AND PUBLIC ROOMS.pdf (2.6MB ^) | XXXX-XXX-02340-001-MA-EN_01--FRESH WATER PIPING LAYOUT - INVENTORY AND PUBLIC ROOMS.dwg (17.4MB ^) | -/- | -/- |  | -/- | Jane Doe | Platform | NA-without | -/- | PAR-Platform Architectural | '=T001-=T001 | - =T001.AZA10-AZA10 - =T001.AXD30-AXD30 | - =T001.AZA10.VQ001-VQ001 - =T001.AZA10.EB003-EB003 - =T001.AZA10.EB002-EB002 - =T001.AZA10.EB001-EB001 - =T001.AXD30.WP117-WP117 - =T001.AXD30.WP116-WP116 - =T001.AXD30.WP115-WP115 - =T001.AXD30.WP114-WP114 - =T001.AXD30.WP113-WP113 - =T001.AXD30.WP112-WP112 - =T001.AXD30.WP111-WP111 - =T001.AXD30.WP110-WP110 - =T001.AXD30.WP109-WP109 - =T001.AXD30.WP108-WP108 - =T001.AXD30.WP107-WP107 - =T001.AXD30.WP104-WP104 - =T001.AXD30.WP103-WP103 - =T001.AXD30.WP106-WP106 - =T001.AXD30.WP105-WP105 - =T001.AXD30.WP101-WP101 | - =T001.AZA10.VQ001.-VQ006--VQ006 - =T001.AZA10.VQ001.-VQ005--VQ005 - =T001.AZA10.VQ001.-VQ004--VQ004 - =T001.AZA10.VQ001.-VQ003--VQ003 - =T001.AZA10.VQ001.-VQ002--VQ002 - =T001.AZA10.VQ001.-VQ001--VQ001 - =T001.AZA10.EB003.-EB001--EB001 - =T001.AZA10.EB002.-EB001--EB001 - =T001.AZA10.EB001.-EB001--EB001 - =T001.AXD30.WP117.-QM001--QM001 - =T001.AXD30.WP116.-RM001--RM001 - =T001.AXD30.WP116.-QM004--QM004 - =T001.AXD30.WP116.-QM003--QM003 - =T001.AXD30.WP116.-QM002--QM002 - =T001.AXD30.WP116.-QM001--QM001 - =T001.AXD30.WP115.-RM001--RM001 - =T001.AXD30.WP115.-QM004--QM004 - =T001.AXD30.WP115.-QM003--QM003 - =T001.AXD30.WP115.-QM002--QM002 - =T001.AXD30.WP115.-QM001--QM001 - =T001.AXD30.WP114.-RM001--RM001 - =T001.AXD30.WP114.-QM004--QM004 - =T001.AXD30.WP114.-QM003--QM003 - =T001.AXD30.WP114.-QM002--QM002 - =T001.AXD30.WP114.-QM001--QM001 - =T001.AXD30.WP113.-QM003--QM003 - =T001.AXD30.WP113.-QM002--QM002 - =T001.AXD30.WP113.-QM001--QM001 - =T001.AXD30.WP112.-RM001--RM001 - =T001.AXD30.WP112.-QM002--QM002 - =T001.AXD30.WP112.-QM001--QM001 - =T001.AXD30.WP111.-QM001--QM001 - =T001.AXD30.WP110.-QM001--QM001 - =T001.AXD30.WP109.-RM001--RM001 - =T001.AXD30.WP109.-QM005--QM005 - =T001.AXD30.WP109.-QM004--QM004 - =T001.AXD30.WP109.-QM003--QM003 - =T001.AXD30.WP109.-QM002--QM002 - =T001.AXD30.WP109.-QM001--QM001 - =T001.AXD30.WP108.-QM001--QM001 - =T001.AXD30.WP107.-QM001--QM001 - =T001.AXD30.WP104.-RM001--RM001 - =T001.AXD30.WP104.-QM004--QM004 - =T001.AXD30.WP104.-QM003--QM003 - =T001.AXD30.WP104.-QM002--QM002 - =T001.AXD30.WP104.-QM001--QM001 - =T001.AXD30.WP103.-QM004--QM004 - =T001.AXD30.WP103.-QM003--QM003 - =T001.AXD30.WP103.-QM002--QM002 - =T001.AXD30.WP103.-QM001--QM001 | -/- | - =T001 AZA10 VQ001-VQ006 - WASH BASIN AT MESS - =T001 AZA10 VQ001-VQ005 - SHOWER SET - =T001 AZA10 VQ001-VQ004 - WASH BASIN AT TOILET - =T001 AZA10 VQ001-VQ003 - WASH BASIN AT CHANGE ROOM - =T001 AZA10 VQ001-VQ002 - WASH BASIN AT CHANGE ROOM - =T001 AZA10 VQ001-VQ001 - WASH BASIN AT WORKSHOP ROOM - =T001 AZA10 EB003-EB001 - ELECTRIC HEATER - =T001 AZA10 EB002-EB001 - ELECTRIC HEATER - =T001 AZA10 EB001-EB001 - ELECTRIC HEATER - =T001 AXD30 WP117-QM001 - MANUAL VALVE - =T001 AXD30 WP116-RM001 - CHECK VALVE - =T001 AXD30 WP116-QM004 - DRAIN VALVE - =T001 AXD30 WP116-QM003 - DRAIN VALVE - =T001 AXD30 WP116-QM002 - DRAIN VALVE - =T001 AXD30 WP116-QM001 - MANUAL VALVE - =T001 AXD30 WP115-RM001 - CHECK VALVE - =T001 AXD30 WP115-QM004 - DRAIN VALVE - =T001 AXD30 WP115-QM003 - DRAIN VALVE - =T001 AXD30 WP115-QM002 - DRAIN VALVE - =T001 AXD30 WP115-QM001 - MANUAL VALVE - =T001 AXD30 WP114-RM001 - CHECK VALVE - =T001 AXD30 WP114-QM004 - DRAIN VALVE - =T001 AXD30 WP114-QM003 - DRAIN VALVE - =T001 AXD30 WP114-QM002 - DRAIN VALVE - =T001 AXD30 WP114-QM001 - MANUAL VALVE - =T001 AXD30 WP113-QM003 - DRAIN VALVE - =T001 AXD30 WP113-QM002 - DRAIN VALVE - =T001 AXD30 WP113-QM001 - MANUAL VALVE - =T001 AXD30 WP112-RM001 - CHECK VALVE - =T001 AXD30 WP112-QM002 - DRAIN VALVE - =T001 AXD30 WP112-QM001 - MANUAL VALVE - =T001 AXD30 WP111-QM001 - MANUAL VALVE - =T001 AXD30 WP110-QM001 - MANUAL VALVE - =T001 AXD30 WP109-RM001 - CHECK VALVE - =T001 AXD30 WP109-QM005 - DRAIN VALVE - =T001 AXD30 WP109-QM004 - DRAIN VALVE - =T001 AXD30 WP109-QM003 - DRAIN VALVE - =T001 AXD30 WP109-QM002 - DRAIN VALVE - =T001 AXD30 WP109-QM001 - MANUAL VALVE - =T001 AXD30 WP108-QM001 - MANUAL VALVE - =T001 AXD30 WP107-QM001 - MANUAL VALVE - =T001 AXD30 WP104-RM001 - CHECK VALVE - =T001 AXD30 WP104-QM004 - DRAIN VALVE - =T001 AXD30 WP104-QM003 - DRAIN VALVE - =T001 AXD30 WP104-QM002 - DRAIN VALVE - =T001 AXD30 WP104-QM001 - MANUAL VALVE - =T001 AXD30 WP103-QM004 - DRAIN VALVE - =T001 AXD30 WP103-QM003 - DRAIN VALVE - =T001 AXD30 WP103-QM002 - DRAIN VALVE - =T001 AXD30 WP103-QM001 - MANUAL VALVE - =T001 AXD30 WP106 - FRESH WATER RETURN LINE TO PUBLIC ROOMS - =T001 AXD30 WP105 - FRESH WATER SUPPLY LINE TO PUBLIC ROOMS - =T001 AXD30 WP101 - FRESH WATER SUPPLY LINE TO WORKSHOP | M - Mechanical engineering | LU010-Arrangement drawing (equipment) | OS00008-E-T001-PI-LTD-34007 | Issued As-Built | For information | B5b-Design- and Construction Documentation - Systems | -/- | -/- | -/- | 001 | -/- | Jane Doe | '=T001 AZA10 VQ001-VQ006 - WASH BASIN AT MESS =T001 AZA10 VQ001-VQ005 - SHOWER SET =T001 AZA10 VQ001-VQ004 - WASH BASIN AT TOILET =T001 AZA10 VQ001-VQ003 - WASH BASIN AT CHANGE ROOM =T001 AZA10 VQ001-VQ002 - WASH BASIN AT CHANGE ROOM =T001 AZA10 VQ001-VQ001 - WASH BASIN AT WORKSHOP ROOM =T001 AZA10 EB003-EB001 - ELECTRIC HEATER =T001 AZA10 EB002-EB001 - ELECTRIC HEATER =T001 AZA10 EB001-EB001 - ELECTRIC HEATER =T001 AXD30 WP117-QM001 - MANUAL VALVE =T001 AXD30 WP116-RM001 - CHECK VALVE =T001 AXD30 WP116-QM004 - DRAIN VALVE =T001 AXD30 WP116-QM003 - DRAIN VALVE =T001 AXD30 WP116-QM002 - DRAIN VALVE =T001 AXD30 WP116-QM001 - MANUAL VALVE =T001 AXD30 WP115-RM001 - CHECK VALVE =T001 AXD30 WP115-QM004 - DRAIN VALVE =T001 AXD30 WP115-QM003 - DRAIN VALVE =T001 AXD30 WP115-QM002 - DRAIN VALVE =T001 AXD30 WP115-QM001 - MANUAL VALVE =T001 AXD30 WP114-RM001 - CHECK VALVE =T001 AXD30 WP114-QM004 - DRAIN VALVE =T001 AXD30 WP114-QM003 - DRAIN VALVE =T001 AXD30 WP114-QM002 - DRAIN VALVE =T001 AXD30 WP114-QM001 - MANUAL VALVE =T001 AXD30 WP113-QM003 - DRAIN VALVE =T001 AXD30 WP113-QM002 - DRAIN VALVE =T001 AXD30 WP113-QM001 - MANUAL VALVE =T001 AXD30 WP112-RM001 - CHECK VALVE =T001 AXD30 WP112-QM002 - DRAIN VALVE =T001 AXD30 WP112-QM001 - MANUAL VALVE =T001 AXD30 WP111-QM001 - MANUAL VALVE =T001 AXD30 WP110-QM001 - MANUAL VALVE =T001 AXD30 WP109-RM001 - CHECK VALVE =T001 AXD30 WP109-QM005 - DRAIN VALVE =T001 AXD30 WP109-QM004 - DRAIN VALVE =T001 AXD30 WP109-QM003 - DRAIN VALVE =T001 AXD30 WP109-QM002 - DRAIN VALVE =T001 AXD30 WP109-QM001 - MANUAL VALVE =T001 AXD30 WP108-QM001 - MANUAL VALVE =T001 AXD30 WP107-QM001 - MANUAL VALVE =T001 AXD30 WP104-RM001 - CHECK VALVE =T001 AXD30 WP104-QM004 - DRAIN VALVE =T001 AXD30 WP104-QM003 - DRAIN VALVE =T001 AXD30 WP104-QM002 - DRAIN VALVE =T001 AXD30 WP104-QM001 - MANUAL VALVE =T001 AXD30 WP103-QM004 - DRAIN VALVE =T001 AXD30 WP103-QM003 - DRAIN VALVE =T001 AXD30 WP103-QM002 - DRAIN VALVE =T001 AXD30 WP103-QM001 - MANUAL VALVE =T001 AXD30 WP106 - FRESH WATER RETURN LINE TO PUBLIC ROOMS =T001 AXD30 WP105 - FRESH WATER SUPPLY LINE TO PUBLIC ROOMS =T001 AXD30 WP101 - FRESH WATER SUPPLY LINE TO WORKSHOP | Related Certification Reply Sheet | Not submitted | -/- | 2022-05-24 | NA | -/-
VENDOR DATASHEET - ELECTRIC WATER HEATER | XXXX-XXX-PET-07805-001 | 2022-11-26 | 01-v001 | Unchecked | -/- | 000-Without | XXXX-XXX-07805-001-MA-EN_01--VENDOR DATASHEET - ELECTRIC WATER HEATER.pdf (2.7MB ^) | -/- | -/- | -/- |  | -/- | Max Mustermann | Platform | NA-without | -/- | PAR-Platform Architectural | '=T001-=T001 | '=T001.AZA10-AZA10 | - =T001.AZA10.EB003-EB003 - =T001.AZA10.EB002-EB002 - =T001.AZA10.EB001-EB001 | - =T001.AZA10.EB003.-EB001--EB001 - =T001.AZA10.EB002.-EB001--EB001 - =T001.AZA10.EB001.-EB001--EB001 | -/- | - =T001 AZA10 EB003-EB001 - ELECTRIC HEATER - =T001 AZA10 EB002-EB001 - ELECTRIC HEATER - =T001 AZA10 EB001-EB001 - ELECTRIC HEATER | M - Mechanical engineering | DA010-Data Sheet | OS00008-E-T001-ST-DTS-08178 | Issued As-Final | For information | B5b-Design- and Construction Documentation - Systems | -/- | -/- | -/- | 001 | -/- | Max Mustermann | -/- | Related Certification Reply Sheet | Not submitted | -/- | 2022-11-28 | NA | -/-